## Milestones
[5 empty] | Year | 2023 | [9 empty] | 2024
[5 empty] | Month | Oct |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar
[5 empty] | Week | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
[5 empty] | Day | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon
|  | Gantt Chart Project Requirement to Project Milestone to Code |  | Start | End | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11
Rubic # | Project Item | Task Name | Complete Percentage |  | This Week | [20 empty] | ▼
| Part 1 - Background Study |  | 100% | 2023-10-23 | 2023-12-01
1 | Study the three Projects | Identify the purpose and logic flow of the three projects Progress : done | 100% | 2023-10-23 | 2023-10-26
|  | Identify the projects to be extended Progress : done | 100% | 2023-10-26 | 2023-11-20
2 | Anslysis of possible extensions | For drawing app Progress : done | 100% | 2023-10-26 | 2023-11-05
|  | For data visualisation app Progress : done, for the mp3 player outlook | 100% | 2023-11-06 | 2023-11-12
|  | For music visualisation app Progress : done, for the six visuals | 100% | 2023-11-12 | 2023-11-19
3 | Set up possible extensions of selected project | Study for possible visualisations Progress : done, decided to make six visuals | 100% | 2023-11-20 | 2023-11-26
|  | Plan for structuring and coding of visualisations Progress : the fifth and sixth visuals are not yet designed | 100% | 2023-11-20 | 2023-12-01
| Part 2 - App System Design |  | 100% | 2023-11-27 | 2024-01-15
4 | Study for applicable functionalities | Study for music player designs Progress : done | 100% | 2023-11-27 | 2023-12-10
|  | Study for implementation of the music visuals to fit into the project Progress : the fifth and sixth visuals are not yet studied | 100% | 2023-12-04 | 2023-12-17
5 | System Design and Analysis | Identify the system objects and set up object classes (with Class Diagram) Progress : done for the music player and the first four visuals (need update after Midterm submission) | 100% | 2023-12-11 | 2023-12-17
|  | Set up object Class Diagram with its structure Progress : need to add visual 5 and 6 class diagram | 100% | 2023-12-18 | 2023-12-24
|  | Summarse the should-have items of each objects structures | 100% | 2023-12-11 | 2024-01-15
| Part 3 - Spiral Development Mode |  | 100% | 2023-11-27 | 2024-02-25
6 | Music Player | Code the project layout Progress : done for the first four, need upgrade and add visual 5 and 6 | 100% | 2023-11-27 | 2023-12-03
|  | Code the music player layout and add buttons Progress : done except volume bar | 100% | 2023-12-04 | 2023-12-10
7 | Music Visualiser | Extend the visualiser objects from base cases Progress : done for the first four visuals | 100% | 2023-12-11 | 2023-12-17
|  | Code the visuals Progress : done for the first four visuals | 100% | 2023-12-18 | 2024-01-21
8 | Project Upgrade | Upgrade the music player outlook | 100% | 2024-01-22 | 2024-01-28
|  | Upgrade the visuals | 100% | 2024-01-09 | 2024-02-04
9 | System Integration | Integrate the Objects and their designes | 100% | 2024-02-05 | 2024-02-18
|  | Reflect and update on the system infrastructure | 100% | 2024-02-19 | 2024-02-25
| Part 4 - System Cutover |  | 100% | 2024-02-19 | 2024-03-11
10 | Test the Project | Unit test the classes | 100% | 2024-02-19 | 2024-02-25
|  | Unit test the functional objects and interactions between tasks | 100% | 2024-02-26 | 2024-03-03
|  | Reflect on the test results and debug | 100% | 2024-03-04 | 2024-03-11

## OverallStructure (hidden)
HTML
dependencies
p5.js
p5.sound
p5.app
skecth.js
music_player
fourier
sound
vis
buttons
controls

## ClassDIagram (hidden)
Button
----------------------------
- x : integer
- y : integer
- width : integer
- height : integer
+ drawStrategy : drawStrategy
+ hitCheckStrategy : hitCheckStrategy
+ draw() : void
+ hitCheck() : boolean
- setPosition(int, int, int, int) : void
ControlsAndInput
-------------------------------------------
+ buttons : Button[]
+ mousePressed() : boolean
+ keyPressed(int) : void
+ draw() : void
- menu() : void
+ menuDisplayed : boolean
+ isPlaying : boolean
PlaybackAndPauseDrawStrategy implements Button
------------------------------------------
+ x : integer
+ y : integer
+ width : integer
+ height : integer
+ draw() : void
PlaybackAndPauseHitCheckStrategy implements Button
---------------------------------------------
+ x : integer
+ y : integer
+ width : integer
+ height : integer
+ hitCheck() : boolean
PlaySpeedDrawStrategy implements Button
--------------------------------
+ x : integer
+ y : integer
+ width : integer
+ height : integer
+ buttonType : string
+ draw() : void
PlaySpeedHitCheckStrategy implements Button
-------------------------------------
+ x : integer
+ y : integer
+ width : integer
+ height : integer
+ buttonType : string
+ hitCheck() : boolean
Sound
---------------------
+ soundSource : sound[]
+ sounds[]
+ playingSound : integer
+ playSpeed : float
+ playVolume : float
+ playing : boolean
+ loadSound() : void
n Aggregation
All are Inheritance of drawStrategy
drawStrategy
All are Inheritance of hitCheckStrategy
1 : 1 each
p5.app
----------------------------
+ mouseClicked() : void
+ keyPressed() : void
+ windowResized() : void
+ draw() : void
+ preload() : void
+ setup() : void
+ fourier : FFT
+ vis : Visualisations
... (skipped the global variables)
Fourier
Visualisations
-------------------
+ visuals : visual[]
+ selectedVisual : visual
+ add(visual) : void
+ selectVisual(string) : void
Music_Player_Frame
----------------------------------
- upFrame : UpperFrame
- lowFrame : LowerFrame
+ draw() : void
1 : 1
UpperFrame
----------------------------------
- frameWidth : Integer
- frameHeight: Integer
- fileName : string
+ draw() : void
- drawLogo() : void
- drawCornerButton () : void
LowerFrame
----------------------------------
- frameWidth : Integer
- frameHeight: Integer
- timeDisplay : TimeDisplay
+ draw() : void
TimeDisplay
----------------------------------
- musicCurrentTime : p5.sound currentTime()
- musicDuration : p5.sound duration()
- yPos : Integer
+ draw() : void
+ setY(integer) : void
1 : 1
1 : 1
1 : 1
WavePattern
--------------------
+ name : string
+ draw() : void
Spectrum
----------------
- spectrum : fourier.analyze()
+ name: string
+ draw() : void
- drawMountain() : void
- drawGradientBackground() : void
+ setSpectrum() : void
Star
-----------
- origin : Vector
- center : Vector
- oppositeCorner : Vector
- starColor : color
- size : Integer
+ draw() :void
+ updatePos() : void
- updatePosX() : void
- updatePosY() : void
Needles
---------------
+ name: string
- radius : Integer
- energy : Integer
+ frequencies : string[]
+ rainbow : color[]
+ draw() : void
+ ticks() : void
Mountain
---------------
- x : Integer
- y : Integer
- width : Integer
- height : Integer
+ draw() : void
1 : 1
1 : 1
1 : n
Particle
--------------------
- position : Vector
- velocity : Vector
- acceleration : Float
- color : color
+ draw() : void
+ update(color, boolean) : void
+ isBoundry() : boolean
1 : 1
1 : n
1 : 1
Phyllotaxis
---------------
+ name: string
- c : Integer
- n : Integer
- expansionAngle : float
+ draw() : void
- clearDots() : void
1 : 1
hitCheckStrategy